## Gantt Chart
Online Movie Ticket Booking System — Sprint 1 Gantt Chart
Sprint window: Aug 9 – Aug 19, 2026 ¦ Gray = est. dev days, Green = passing test, Red = failing test
User Story ID | Story Name | Status | Aug 09 | Aug 10 | Aug 11 | Aug 12 | Aug 13 | Aug 14 | Aug 15 | Aug 16 | Aug 17 | Aug 18 | Aug 19 | Color Key
US-01 | Search Movies by City | Done | Dev | Dev | P | P |  | P |  | P |  |  |  |  | Estimated Dev Days
US-02 | View Showtimes | Testing | [12 empty] | Passing Test
US-03 | Select Seats | Done | Dev | Dev | P | P |  |  | P | [5 empty] | Failing Test
US-04 | Apply Promo Code | Done |  |  | Dev | Dev | P | P |  | P |  |  |  |  | No Activity (blank)
US-05 | Online Payment Gateway | Testing |  |  |  | Dev | Dev | F |  |  |  | F
US-06 | Generate E-Ticket | Sprint 1 | [11 empty] | Status Key
US-07 | Cancel Booking | Backlog | [12 empty] | Done
US-08 | Booking History | Backlog | [12 empty] | Testing
US-09 | Email Notification | Backlog | [12 empty] | Sprint 1
US-10 | Rate & Review Movie | Testing |  |  |  |  | Dev | Dev | P |  | P |  |  |  | Backlog
Test Case Matrix
User Story ID | Test Date | Result
US-01 | 2026-08-11 | Pass
US-01 | 2026-08-12 | Pass
US-01 | 2026-08-14 | Pass
US-01 | 2026-08-16 | Pass
US-03 | 2026-08-11 | Pass
US-03 | 2026-08-12 | Pass
US-03 | 2026-08-15 | Pass
US-04 | 2026-08-13 | Pass
US-04 | 2026-08-14 | Pass
US-04 | 2026-08-16 | Pass
US-05 | 2026-08-14 | Fail
US-05 | 2026-08-18 | Fail
US-10 | 2026-08-15 | Pass
US-10 | 2026-08-17 | Pass
Summary — Test Results by User Story
User Story ID | Total Tests | Passed | Failed
US-01 | 4 | 4 | 0
US-02 | 0 | 0 | 0
US-03 | 3 | 3 | 0
US-04 | 3 | 3 | 0
US-05 | 2 | 0 | 2
US-06 | 0 | 0 | 0
US-07 | 0 | 0 | 0
US-08 | 0 | 0 | 0
US-09 | 0 | 0 | 0
US-10 | 2 | 2 | 0
SPRINT TOTAL | 14 | 12 | 2