## Sprint1
Sprint 1 Plan
Sprint Goal: Deliver core account management and initiate movie browsing, seat selection, and payment modules.
Task ID | Task Description | Related User Story | Assigned To | Role | Story Points | Status | Deadline
T-01 | Design & implement registration/login UI wireframe | US-01 | Aayushma Karki | Designer | 1 | Done | 2026-03-10
T-02 | Define auth data model & validation rules (doc) | US-01 | Suman Pandey | Developer | 1 | Done | 2026-03-10
T-03 | Write functional requirements for movie browsing | US-02 | Suman Pandey | Developer | 1 | Done | 2026-03-11
T-04 | Design movie listing & filter mockups | US-02 | Aayushma Karki | Designer | 2 | In Progress | 2026-03-13
T-05 | Design seat map layout mockup | US-03 | Aayushma Karki | Designer | 2 | In Progress | 2026-03-13
T-06 | Document seat locking business logic | US-03 | Suman Pandey | Developer | 2 | In Progress | 2026-03-14
T-07 | Draft payment gateway integration requirements | US-04 | Suman Pandey | Developer | 3 | To Do | 2026-03-15
T-08 | Create Use Case & Class diagrams | US-01–US-04 | Suman Pandey | Developer | 3 | In Progress | 2026-03-15
T-09 | Create Sequence & Activity diagrams | US-03, US-04 | Suman Pandey | Developer | 3 | To Do | 2026-03-16
T-10 | Set up GitHub repository & folder structure | All | Suman Pandey | Developer | 1 | Done | 2026-03-09
T-11 | Design booking history screen | US-06 | Aayushma Karki | Designer | 1 | Done | 2026-03-12
T-12 | Write unit & integration test cases for auth and seat locking | US-01, US-03 | Salina Tiwari | Tester | 2 | In Progress | 2026-03-15
T-13 | Sprint 1 review & retrospective | All | Full Team | All | 1 | To Do | 2026-03-16
Team Roles
Name | Role | Responsibilities
Suman Pandey | Developer | Requirement docs, UML diagrams, GitHub repo structure & version control, sprint facilitation
Aayushma Karki | Designer | Wireframes, screen mockups, seat map & payment UI design
Salina Tiwari | Tester | Test case design & execution across Unit, Integration, System, and UAT levels