## product backlog
Online Movie Ticket Booking System — Product Backlog
ID | User Story | Epic | Story Points | Priority | Status | Sprint | Acceptance Criteria
US-01 | As a customer, I want to register and log in so that I can manage my bookings securely. | Account Management | 3 | High | Done | Sprint 1 | User can sign up with email/phone, verify account, and log in/out; invalid credentials show an error.
US-02 | As a customer, I want to browse movies and showtimes by cinema, date, and genre so that I can find a film to watch. | Movie Browsing | 5 | High | In Progress | Sprint 1 | Movie list loads with poster, genre, rating, and available showtimes; filters work correctly.
US-03 | As a customer, I want to select seats from a visual seat map so that I can choose where I sit. | Booking | 5 | High | In Progress | Sprint 1 | Seat map shows booked/available/selected seats in real time; max seats per booking enforced.
US-04 | As a customer, I want to pay online securely so that I can complete my ticket purchase. | Payment | 8 | High | To Do | Sprint 1 | Payment gateway processes card/wallet payment; success/failure is handled and confirmed to the user.
US-05 | As a customer, I want to cancel a booking before the showtime so that I can get a refund if needed. | Booking | 3 | Medium | To Do | Sprint 1 | Cancellation allowed up to 2 hours before showtime; refund request is generated automatically.
US-06 | As a customer, I want to view my booking history so that I can track my past and upcoming bookings. | Account Management | 2 | Medium | Done | Sprint 1 | List of bookings with movie, date, seats, and status is shown, sorted by most recent.
US-07 | As a customer, I want to apply a promo code at checkout so that I can get a discount. | Payment | 3 | Low | To Do | Backlog | Valid codes reduce total price; invalid/expired codes show a clear error message.
US-08 | As a customer, I want to rate and review a movie after watching it so that I can share feedback. | Engagement | 2 | Low | To Do | Backlog | User can submit a 1–5 star rating and comment once per booked movie.
US-09 | As a customer, I want to receive push/email notifications for booking confirmation and reminders. | Notifications | 3 | Medium | To Do | Backlog | Confirmation is sent immediately after booking; reminder is sent 2 hours before showtime.
US-10 | As an admin, I want to manage movies, showtimes, and view sales reports so that I can run cinema operations. | Admin | 5 | High | To Do | Backlog | Admin can add/edit/delete movies and showtimes; sales report is exportable by date range.